## ProductionPlan
material | location | line | simulation_date | production_plan_date | available_date | uncon_planned_qty | con_planned_qty | produced_qty | changeover_id | changeover_time | changeover_time_remaining | is_first_changeover_day
80848023 | 0386 | TPOCPACK | 2025-12-27 | 2025-12-30 | 2026-01-03 | 4008 | 4008 | 3623 | Change over
21377504 | 0386 | TPOCPACK | 2025-12-27 | 2025-12-30 | 2025-12-30 | 2500 | 2500 | 2261 | Change batch
21434946 | 0386 | TPOCPACK | 2025-12-27 | 2025-12-30 | 2025-12-30 | 1838 | 92 | 86 | Change batch
21143102 | 0386 | TPODPACK | 2025-12-27 | 2025-12-30 | 2025-12-30 | 1020 | 1020 | 935 | Washout_changeover
80807092 | 0386 | TPODPACK | 2025-12-27 | 2025-12-30 | 2026-01-03 | 1416 | 1416 | 1306 | Washout
21143103 | 0386 | TPODPACK | 2025-12-27 | 2025-12-30 | 2025-12-30 | 903 | 903 | 817 | Washout
21128067 | 0386 | TPODPACK | 2025-12-27 | 2025-12-30 | 2025-12-30 | 2043 | 41 | 39 | Washout_changeover
80804703 | 0386 | TPOFPACK | 2025-12-27 | 2025-12-30 | 2026-01-03 | 4031 | 3335 | 2999 | Washout_changeover
21137866 | 0386 | TPOGPACK | 2025-12-27 | 2025-12-30 | 2025-12-30 | 3443 | 3443 | 3102 | Washout_changeover
21148509 | 0386 | TPOGPACK | 2025-12-27 | 2025-12-30 | 2025-12-30 | 1588 | 1588 | 1421 | Washout
21132758 | 0386 | TPOGPACK | 2025-12-27 | 2025-12-30 | 2025-12-30 | 2098 | 973 | 886 | Change over

## CapacityExceed
material | location | line | simulation_date | exceed_type | exceed_qty
21434946 | 0386 | TPOCPACK | 2025-12-27
80848026 | 0386 | TPOCPACK | 2025-12-27
21314602 | 0386 | TPOCPACK | 2025-12-27
21434952 | 0386 | TPOCPACK | 2025-12-27
80863646 | 0386 | TPOCPACK | 2025-12-27
21434954 | 0386 | TPOCPACK | 2025-12-27
80863645 | 0386 | TPOCPACK | 2025-12-27
80884850 | 0386 | TPOCPACK | 2025-12-27
80848022 | 0386 | TPOCPACK | 2025-12-27
21304907 | 0386 | TPOCPACK | 2025-12-27
21291975 | 0386 | TPOCPACK | 2025-12-27
21422791 | 0386 | TPOCPACK | 2025-12-27
21419500 | 0386 | TPOCPACK | 2025-12-27
80885921 | 0386 | TPOCPACK | 2025-12-27
80804698 | 0386 | TPOCPACK | 2025-12-27
80804699 | 0386 | TPOCPACK | 2025-12-27
80804704 | 0386 | TPOCPACK | 2025-12-27
80804705 | 0386 | TPOCPACK | 2025-12-27
80793615 | 0386 | TPOCPACK | 2025-12-27
80796091 | 0386 | TPOCPACK | 2025-12-27
80795933 | 0386 | TPOCPACK | 2025-12-27
80793614 | 0386 | TPOCPACK | 2025-12-27
21303404 | 0386 | TPOCPACK | 2025-12-27
80848021 | 0386 | TPOCPACK | 2025-12-27
80848024 | 0386 | TPOCPACK | 2025-12-27
21118867 | 0386 | TPOCPACK | 2025-12-27
80804131 | 0386 | TPOCPACK | 2025-12-27
80885919 | 0386 | TPOCPACK | 2025-12-27
80804702 | 0386 | TPOCPACK | 2025-12-27
80854083 | 0386 | TPOCPACK | 2025-12-27
80804127 | 0386 | TPOCPACK | 2025-12-27
80868100 | 0386 | TPOCPACK | 2025-12-27
80823707 | 0386 | TPOCPACK | 2025-12-27
80884845 | 0386 | TPOCPACK | 2025-12-27
21354246 | 0386 | TPOCPACK | 2025-12-27
80848028 | 0386 | TPOCPACK | 2025-12-27
80807114 | 0386 | TPOCPACK | 2025-12-27
80812110 | 0386 | TPOCPACK | 2025-12-27
80804701 | 0386 | TPOCPACK | 2025-12-27
80840976 | 0386 | TPOCPACK | 2025-12-27
80840975 | 0386 | TPOCPACK | 2025-12-27
21301637 | 0386 | TPOCPACK | 2025-12-27
21128067 | 0386 | TPODPACK | 2025-12-27
80804134 | 0386 | TPODPACK | 2025-12-27
80804703 | 0386 | TPOFPACK | 2025-12-27
80804706 | 0386 | TPOFPACK | 2025-12-27
21352461 | 0386 | TPOFPACK | 2025-12-27
80868102 | 0386 | TPOFPACK | 2025-12-27
21357275 | 0386 | TPOFPACK | 2025-12-27
80868101 | 0386 | TPOFPACK | 2025-12-27
21170683 | 0386 | TPOFPACK | 2025-12-27
80804137 | 0386 | TPOFPACK | 2025-12-27
21121752 | 0386 | TPOFPACK | 2025-12-27
21165816 | 0386 | TPOFPACK | 2025-12-27
80804128 | 0386 | TPOFPACK | 2025-12-27
80807100 | 0386 | TPOFPACK | 2025-12-27
21176384 | 0386 | TPOFPACK | 2025-12-27
80804130 | 0386 | TPOFPACK | 2025-12-27
21113405 | 0386 | TPOFPACK | 2025-12-27
80848027 | 0386 | TPOFPACK | 2025-12-27
21139445 | 0386 | TPOFPACK | 2025-12-27
21132758 | 0386 | TPOGPACK | 2025-12-27
80807116 | 0386 | TPOGPACK | 2025-12-27
21179704 | 0386 | TPOGPACK | 2025-12-27
21128377 | 0386 | TPOGPACK | 2025-12-27
80807115 | 0386 | TPOGPACK | 2025-12-27
21141769 | 0386 | TPOGPACK | 2025-12-27
21132988 | 0386 | TPOGPACK | 2025-12-27
80807096 | 0386 | TPOGPACK | 2025-12-27
21315474 | 0386 | TPOGPACK | 2025-12-27
21314593 | 0386 | TPOGPACK | 2025-12-27
21315352 | 0386 | TPOGPACK | 2025-12-27
80848029 | 0386 | TPOGPACK | 2025-12-27
21314875 | 0386 | TPOGPACK | 2025-12-27
21314594 | 0386 | TPOGPACK | 2025-12-27
80848025 | 0386 | TPOGPACK | 2025-12-27
21314876 | 0386 | TPOGPACK | 2025-12-27
21325164 | 0386 | TPOGPACK | 2025-12-27
21314595 | 0386 | TPOGPACK | 2025-12-27
80848031 | 0386 | TPOGPACK | 2025-12-27
21447518 | 0386 | TPOGPACK | 2025-12-27
21269899 | 0386 | TPOGPACK | 2025-12-27
80807122 | 0386 | TPOGPACK | 2025-12-27
80865910 | 0386 | TPOGPACK | 2025-12-27
80838164 | 0386 | TPOGPACK | 2025-12-27
80838165 | 0386 | TPOGPACK | 2025-12-27
80838162 | 0386 | TPOGPACK | 2025-12-27
80812338 | 0386 | TPOGPACK | 2025-12-27

## Validation
type | location | line | production_plan_date | simulation_date | previously_allocated_hours | currently_allocated_hours | total_allocated_hours | message | issue | sheet | row

## ChangeoverLog
date | location | line | changeover_type | count | time | cost | mu_loss
2025-12-30 | 0386 | TPOCPACK | Change batch | 2 | 1 | 1126 | 0
2025-12-30 | 0386 | TPOCPACK | Change over | 1 | 1 | 931 | 0
2025-12-30 | 0386 | TPODPACK | Washout | 2 | 1.3333 | 3384 | 0.032069
2025-12-30 | 0386 | TPODPACK | Washout_changeover | 2 | 1.5 | 3556 | 0.032069
2025-12-30 | 0386 | TPOFPACK | Washout_changeover | 1 | 1 | 1505 | 0.0081034
2025-12-30 | 0386 | TPOGPACK | Change over | 1 | 1 | 931 | 0
2025-12-30 | 0386 | TPOGPACK | Washout | 1 | 1 | 3582 | 0.030172
2025-12-30 | 0386 | TPOGPACK | Washout_changeover | 1 | 1.1667 | 3905 | 0.030172