## ProductionPlan
material | location | line | simulation_date | production_plan_date | available_date | uncon_planned_qty | con_planned_qty | produced_qty | changeover_id | changeover_time | changeover_time_remaining | is_first_changeover_day
80848026 | 0386 | TPOCPACK | 2026-01-20 | 2026-01-23 | 2026-01-27 | 4008 | 4008 | 3623 | Washout
21434952 | 0386 | TPOCPACK | 2026-01-20 | 2026-01-23 | 2026-01-23 | 2500 | 2500 | 2261 | Washout
80804132 | 0386 | TPODPACK | 2026-01-20 | 2026-01-23 | 2026-01-27 | 2792 | 2792 | 2567 | Washout_changeover
80805856 | 0386 | TPOEPACK | 2026-01-20 | 2026-01-23 | 2026-01-27 | 1500 | 1500 | 1367 | Washout_changeover
80805852 | 0386 | TPOEPACK | 2026-01-20 | 2026-01-23 | 2026-01-27 | 334 | 334 | 308 | Washout_changeover
80812841 | 0386 | TPOGPACK | 2026-01-20 | 2026-01-23 | 2026-01-27 | 4292 | 4292 | 3857 | Washout_changeover
80807116 | 0386 | TPOGPACK | 2026-01-20 | 2026-01-23 | 2026-01-27 | 5968 | 2407 | 2164 | Change batch
80812840 | 0386 | TPOGPACK | 2026-01-20 | 2026-01-24 | 2026-01-28 | 3886 | 3886 | 3501 | Change batch

## CapacityExceed
material | location | line | simulation_date | exceed_type | exceed_qty
80848028 | 0386 | TPOCPACK | 2026-01-20
21354246 | 0386 | TPOCPACK | 2026-01-20
80848023 | 0386 | TPOCPACK | 2026-01-20
80812110 | 0386 | TPOCPACK | 2026-01-20
80807116 | 0386 | TPOGPACK | 2026-01-20
21132758 | 0386 | TPOGPACK | 2026-01-20
21179704 | 0386 | TPOGPACK | 2026-01-20
21133312 | 0386 | TPOGPACK | 2026-01-20
21162696 | 0386 | TPOGPACK | 2026-01-20
21151196 | 0386 | TPOGPACK | 2026-01-20
21315474 | 0386 | TPOGPACK | 2026-01-20
21314593 | 0386 | TPOGPACK | 2026-01-20
21447518 | 0386 | TPOGPACK | 2026-01-20
80848029 | 0386 | TPOGPACK | 2026-01-20
21315352 | 0386 | TPOGPACK | 2026-01-20
21314875 | 0386 | TPOGPACK | 2026-01-20
21325164 | 0386 | TPOGPACK | 2026-01-20
80848025 | 0386 | TPOGPACK | 2026-01-20
80848031 | 0386 | TPOGPACK | 2026-01-20

## Validation
type | location | line | production_plan_date | simulation_date | previously_allocated_hours | currently_allocated_hours | total_allocated_hours | message | issue | sheet | row

## ChangeoverLog
date | location | line | changeover_type | count | time | cost | mu_loss
2026-01-23 | 0386 | TPOCPACK | Washout | 2 | 2 | 7164 | 0.060345
2026-01-23 | 0386 | TPODPACK | Washout_changeover | 1 | 0.75 | 1778 | 0.016034
2026-01-23 | 0386 | TPOEPACK | Washout_changeover | 2 | 2.3333 | 6560 | 0.054138
2026-01-23 | 0386 | TPOGPACK | Change batch | 1 | 0.5 | 563 | 0
2026-01-23 | 0386 | TPOGPACK | Washout_changeover | 1 | 1.1667 | 3905 | 0.030172
2026-01-24 | 0386 | TPOGPACK | Change batch | 1 | 0.5 | 563 | 0